## ProjectPlan
Visit Mendocino County: Strategic Direction 2017/18-2019/20
|  |  | Project Start: | 2017-07-01
|  |  | Display: | Monthly
|  |  | Display Period: | 1 | [5 empty] | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01
[10 empty] | 1 Jul '17 | 1 Aug '17 | 1 Sep '17 | 1 Oct '17 | 1 Nov '17 | 1 Dec '17 | 1 Jan '18 | 1 Feb '18 | 1 Mar '18 | 1 Apr '18 | 1 May '18 | 1 Jun '18 | 1 Jul '18 | 1 Aug '18 | 1 Sep '18 | 1 Oct '18 | 1 Nov '18 | 1 Dec '18 | 1 Jan '19 | 1 Feb '19 | 1 Mar '19 | 1 Apr '19 | 1 May '19 | 1 Jun '19 | 1 Jul '19 | 1 Aug '19 | 1 Sep '19 | 1 Oct '19 | 1 Nov '19 | 1 Dec '19 | 1 Jan '20 | 1 Feb '20 | 1 Mar '20 | 1 Apr '20 | 1 May '20 | 1 Jun '20
WBS | TASK DESCRIPTION | ASSIGNED TO | PROGRESS | PLAN START | PLAN END | PLAN DAYS | ACTUAL START | ACTUAL END | ACTUAL DAYS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| IMPERATIVE 1: Demonstrate and strengthen VMC’s contribution to county economic and community vitality OBJECTIVES: • Bid assessment growth at 5% over average of top 3 competitors • Year-over-year increase of sales tax receipts in Mendocino County • Year-over-year increase in stakeholder survey response rate | Team | 25% | 2017-07-01 | 2020-06-30 | 1096 | 2017-07-01 | 2018-07-03 | 368
| INITIATIVE 1: Increase tourism revenue through the development and implementation of the annual integrated marketing, public relations, and sales plan. |  | 33% | 2017-07-01 | 2020-06-30 | 1096 | 2017-07-01 | 2018-07-03 | 368
| Create 2018/19 marketing plan | AdeG | 100% | 2018-04-01 | 2018-05-31 | 61 | 2018-04-01 | 2018-05-31 | 61 | bar: 10 to 11
| Create2018/19 Annual Report | AdeG | 0% | 2018-08-01 | 2018-09-14 | 45
| Create Q4 Report (2017/18) | AdeG | 0% | 2018-08-01 | 2018-09-14 | 45
| Leverage partnerships in tourism. i.e.; NCTC, VCA, SFTA, etc. | RS | Ongoing | 2017-07-01 | 2020-06-30 | 1096 | 2017-07-01 | 2018-07-03 | 368
| Hotel Adoption Program | Team | Ongoing | 2017-07-01 | 2020-06-30 | 1096 | 2017-07-01 | 2018-07-03 | 368 | bar: 1 to 12
| INITIATIVE #2: Improve data-driven decision making through increased participation & "buy in" from all of our partners. |  |  | 2017-07-01 | 2020-06-30 | 1096 | 2017-07-01 | 2018-07-03 | 368
| Distribute monthly PR Update newsletters to stakeholders | AdeG | Ongoing | 2017-07-01 | 2018-07-03 | 368 | 2017-07-01 | 2018-07-03 | 368
| Create Stakeholder one-sheet for distribution | AdeG | 100% | 2017-09-15 | 2017-10-15 | 31 | 2017-09-15 | 2017-10-15 | 31 | bar: 3
| Identify meaningful metrics and proxies with Theory SF | AdeG | Ongoing | 2017-07-01 | 2018-07-03 | 368 | 2017-07-01 | 2018-07-03 | 368
| Identify potential new partners and proactively recruit | Team | Ongoing | 2017-07-01 | 2018-07-03 | 368 | 2017-07-01 | 2018-07-03 | 368
| INITIATIVE #3: Develop a data sharing process that offers context and insights for partners | TEAM |  | 2017-07-01 | 2020-06-30 | 1096 | 2017-07-01 | 2018-07-03 | 368
| Educate Stakeholders about VMC benefits: Hold "town hall" meetings to educate re VMC efforts | TEAM | Ongoing | 2017-07-01 | 2020-06-30 | 1096 | 2017-07-01 | 2018-07-03 | 368
| Refine quarterly report format to correlate to Strategic and Marketing Plans | AdeG | 100% | 2018-04-01 | 2018-04-30 | 30 | 2018-04-01 | 2018-04-30 | 30 | bar: 10
| Create "opportunities" section in stakeholder newsletters | TRS |  | 2018-07-01 | 2020-06-30 | 731 | bar: 10
| Solicit research/data from partners and create a list of partners that have existing data research results | Team | Ongoing | 2017-07-01 | 2020-06-30 | 1096
| IMPERATIVE 2: Cultivate VMC's relationships & collaborations OBJECTIVES: • YOY increase in number of events launched and reaching self sufficiency • YOY increase in “opportunities” page visitation on VMC website • YOY increase in new applicants for BID and MCTC Board positions and committee membership | Team |  | 2017-07-01 | 2018-09-01 | 428 | 2017-12-01 | 2018-05-14 | 165
| Initiative 4: Foster collaboration and county-wide alignment by creating and developing the “go to” website for all tourism stakeholders. | AdeG | 90% | 2017-12-01 | 2018-05-14 | 165 | 2017-12-01 | 2018-05-14 | 165
| Build website wireframe | TSF | 100% | 2017-12-01 | 2017-12-31 | 31 | 2017-12-01 | 2017-12-31 | 31
| Build site | TSF | 100% | 2018-01-01 | 2018-04-01 | 91 | 2018-01-04 | 2018-05-03 | 120
| Alpha & Beta Test; launch site | TSF/AdeG | 100% | 2018-04-02 | 2018-05-14 | 43 | 2018-05-07 | 2018-05-14 | 8
| Develop and test stakeholder reporting | TSF | 5% | 2018-06-13 | 2018-07-13 | 31 | 2018-06-13
| Track and modify/refine based on analytics and user response | TSF/AdeG | ? | 2018-07-03 | 2018-09-01 | 61
| Initiative #5: Strengthen regional tourism relationships to leverage broader marketing opportunities | Team | Ongoing | 2017-07-01 | 2020-06-30 | 1096 | 2017-07-01 | 2018-07-03 | 368
| Audit current regional relationships for ROI; evaluate/prioritize based on results | ? | ? | 2017-07-01 | 2020-06-30 | 1096 | 2017-07-01 | 2018-07-03 | 368
| Create regional itineraries | RS | ? | 2017-07-01 | 2017-10-28 | 120 | 2017-07-01 | 2018-07-03 | 368
| Develop content for Visit CA | AdeG | Ongoing | 2017-07-01 | 2020-06-30 | 1096 | 2017-07-01 | 2018-07-03 | 368
| Develop additional North Coast content | RS | Ongoing | 2017-07-01 | 2020-06-30 | 1096 | 2017-07-01 | 2018-07-03 | 368
| Develop Strategic Plan for North Coast Tourism Council | RS | 100% | 2017-12-01 | 2018-03-31 | 121
| Expand reach with pilot program to develop new partnerships. i.e.: Oakland, Berkley, San Mateo etc. | RS | ? | 2017-07-01
| Initiative #6: Proactively educate and communicate with all tourism stakeholders | Team | Ongoing | 2017-07-01 | 2020-06-30 | 1096 | 2017-07-01 | 2018-07-03 | 368
| Establish hierarchy of stakeholders and targets |  |  | 2017-07-01
| Itemize all communications options ie., 1 on 1: Groups; Shows: Lunch & Learn: etc. |  |  | 2017-07-01
| Establish consistent schedule of outreach/events |  |  | 2017-07-01
| Look into print vehicles (Columns) |  |  | 2017-07-01
| Survey Topics of interest & respond with information/Programming "Pain Points" |  |  | 2017-07-01
| Develop print version with BRC for email capture of lodging recipients |  |  | 2017-07-01
| Scrub distribution list with new additions from County |  |  | 2017-07-01
| ID all meeting schedules / venues held by agencies (Chambers, County Sups,etc.) |  |  | 2017-07-01
| Create bi-monthly e-newsletter (first edition Sept) |  |  | 2017-07-01
| IMPERATIVE 3: Raise awareness of the Mendocino County experience OBJECTIVES: • Year-over-year increase Mendocino County awareness score • Year-over-year increases in impressions and ad equivalency • Year-over-year increase in experience perception score on in-market visitor survey | Team |  | 2017-07-01 | 2018-09-30 | 457 | 2017-10-01 | 2018-07-03 | 276
| Initiative #7: Increase Mendocino County brand awareness and positive perception | AdeG | Ongoing
| Establish & maintain brand standards | AdeG | 100% | 2018-03-01 | 2018-04-14 | 45 | 2018-03-01 | 2018-04-14 | 45
| Develop new marketing, strategies, programs and materials | TSF/AdeG | Ongoing | 2017-10-01 | 2018-09-30 | 365 | 2017-10-01 | 2018-07-03 | 276
| Master Swag List creation and priorities for orders | AdeG/RS | 95% | 2018-05-01 | 2018-07-14 | 75 | 2018-05-01 | 2018-07-03 | 64
| Initiative #8: Work with partners to develop, promote and grow strong and beneficial tourism activities and events | LH | Ongoing
| Disseminate grant info via multiple sources | LH
| Identify upcoming events that VMC can best benefit | LH
| Standard approach to events reporting | LH
| Offer to provide "post mortem" of events | LH
| Create 'One Sheet" re: VMC role in festivals/events (What we offer in support) | LH
| Poll events to determine survey methodology, study and review results | LH
| Initiative #9: Explore our options to influence & shape potential cannabis tourism | Team | 100%
| Transfer responsibility to MCPA | Team | 100% | 2017-07-01 | 2017-12-23 | 176 | 2017-07-01 | 2017-12-21 | 174
Insert new rows ABOVE this one
https://www.vertex42.com/ExcelTemplates/project-planner-template.html
Alison = Gold
Travis = Blue

## Help
HELP
https://www.vertex42.com/ExcelTemplates/project-planner-template.html
© 2017 Vertex42 LLC
About
This project planner template was designed to provide a simple way to create a project schedule with a Gantt chart that shows both planned and actual dates. Other than that, it contains very few features, which may be great if you want something simple.
Want more features?
Learn About Gantt Chart Template Pro
Adding More Rows
When you insert new rows, you should insert a blank row between rows that have the formatting you want. If you do that, the formatting will be copied automatically.
Text Within the Gantt Chart
You can enter text within the gantt chart area, but that text does not move if you adjust the start/end dates or use the scroll bar.
Adding More Columns to the Gantt Chart
If you want to increase the time span shown in chart, you can add columns to the right of the Gantt chart by copying and pasting entire columns.
Conditional Formatting
The bars of the Gantt chart are created using conditional formatting. This spreadsheet is not designed to allow you to change the colors for different bars. Use Gantt Chart Pro if you want to do that.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
Other Templates
Visit Vertex42.com to find other project management templates.
Project Management Templates

## ©
Project Planner Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-planner-template.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.