Visit Mendocino County, Inc. Quarterly Report July - September 2012 Submitted to: Mendocino County Promotional Alliance Mendocino County Lodging Association County Of Mendocino October 9, 2012

The following is a progress report on the goals as outlined in the approved 2012-2013 Marketing Plan

| Project | 2012-2013 Goal | Year Totals | % Complete | Comments |
| --- | --- | --- | --- | --- |
| Print, On-line & Radio Advertising | 40,000,000 Impressions; 10,000 Leads | 29,200,041 Impressions 400 Leads | 73% impressions 4% of leads | Impressions not at full capacity yet – still have $ to spend. Leads low due to only one ad has been placed to date |
| Social Media | 20,000 Fans/10,000 Followers; 1,500 Direct Inquiries | 15,791 Fans/ 1,843 Followers; 322 Direct Inquiries | 78.9% Fans/ 18% Followers; 21% Direct Inquiries |  |
| Email Marketing | 30,000 Subscriptions; | 21,143 Subscriptions; - Clicks; 18.9% Unsubscribe | 73% Subscriptions |  |
| Website | 200,000 Unique Visitors; Includes new website design | 34,832 Unique Visitors 41.34% Bounce Rate Time on site: 00:04:39 | 17.4% Unique Visitors |  |
| Public & Media Relations | 120,840,000 Impressions; $5,000,000 Equivalency | Total Impressions: 48,259,584; $1,837,046 Actual Equivalency | 37% Impressions; 34% Equivalency |  |
| Leisure Sales | 7,000 Direct Consumer Leads | 2,350 Direct Consumer Leads | 34% | Ghirardelli Square Chocolate Festival, Bark in the Park |
| Group Sales | 10 New Contracts | 2 New Contracts | 20% |  |
| Visitor Centers & Signage | Install 1 Gateway Signs; 2 Informational Kiosks; | 0 Gateway Signs; 0 Gateway Kiosks | 0% | Anderson Valley Kiosk is finished. Working on Hwy 20 Gateway sign |
| Visitor Guide & Fulfillment | 2012-2013 Visitor's Guide; Annual Events Calendar; Tear Off Maps | New 2012-2013 Visitor Guides have been printed and are being distributed |  |  |

QUARTERLY ACTIVITIES REPORT JANUARY – MARCH 2012

Visit Mendocino County (VMC) Board, Committees and Staff have been focused on implementing the approved Marketing Plan for 2012-2013.  The following are details on activities & accomplishments supporting the Plan.

Marketing Plan strategic goals are:

- Increase overall visitation to Mendocino County, specifically in the spring and fall shoulder seasons

- Increase length of stay per visitation

- Increase  visitor spending per day

Advertising/Media

- Already at 83% of goal for Facebook likes and growing

- Distributed bi-monthly regional event calendars focusing on key regions and local current events and happenings in an effort to share and attract interest from visitors, businesses and residents alike

- Quarterly requests distributed to listserv to encourage business owners to publish their own listings, with the end goal to list all tourist-related businesses within comprehensive database to be updated on an annual basis to reflect new or revised information.

- Continue to serve on Ukiah TOT committee, “Visit Ukiah”

- Distributed monthly e-blasts promoting annual festivals, events, specials and packages, POIs, etc.

- Developing Fall Radio package.  Currently looking for partners to provide additional exposure and lengthen program

- Using new ad campaign in 2012/2013 media plan.  Feedback has been positive and to date, leads are increasing over last year.

- Submitted new ad campaign for Oyster.com award for most innovative marketing campaign

- Finalized iOS and Android Mobile Phone app.  Already have 1,000 downloads!

- Finalized Visitor Guide content, images, and advertisements and have new and improved guides in-house and ready for distribution

- Finalized the Sunset Sweepstakes package to run in the November issue of Sunset Magazine.  It includes an 11 night tour throughout Mendocino County with at least one stop in each region.  Total donation value exceeds over $4800!

- Completed website content project which added over 400 visitor serving businesses to visitmendocino.com

- Partnered with FlipKey.com to ensure Mendocino County content was available which included a free ad that circulates on the homepage

- Coordinated Mendocino County wines for CA Wine Month tasting in San Francisco, hosted by the Wine Institute.  6 wineries donated wine and 3 wine representatives attended and poured

| Fulfillment Type | July | August | September | Total |
| --- | --- | --- | --- | --- |
| Toll Free Calls | 61 | 101 | 103 | 265 |
| Visitor Guides | 330 | 459 | 393 | 1,182 |

*Waiting on updated visitor guide to distribute leads

Google Analytics for July - September:

|  | 1st Qtr Report 12/13 |  |  | YTD |
| --- | --- | --- | --- | --- |
|  | July | August | September | Total/Avg. |
| Unique Visits | 13,788 | 14,000 | 9,352 | 36,131 |
| No. Page Views | 76,976 | 76,562 | 49,914 | 203,452 |
| Avg. Pages per Visit | 4.56 | 4.47 | 4.31 | 4.46 |
| Avg. Bounce Rate | 40.19% | 41.13% | 43.60% | 41.41% |
| Avg.Time on Site | 00:04:35 | 00:04:24 | 00:04:23 | 0:04:28 |
| % New Visitors | 76.11% | 76.52% | 73.86% | 75.70% |

Public Relations
Mendocino County is in the news! Local, national and international editors and producers continue to feature and visit the County. For this quarter, the public relations team was able to secure many outstanding print and internet clips and even host an international TV crew that broadcast their feature on Gobo TV, the equivalent of CNN in Brazil. Each quarter, this team strives to promote and share stories that journalists will find relevant and timely. This concentration on newsworthiness has always been our mission, and we continue to see our consumer impressions increase. Powerful national media like O, The Oprah Magazine, Fodor’s and Sunset feature tidbits from our “What’s New” press releases. Local media like Sacramento Magazine, 7x7 and the San Francisco Chronicle engage with the local getaway stories. This coming year, our team has built a fresh calendar of news release and unique people and personality pitches that we know will be successful. As always, we look forward to hearing from anyone with unique stories!

Here are a few highlights:

Just some of the media coverage Mendocino County received from July - September 2012:

- edible Marin & Wine Country

- O, The Oprah Magazine

- Fodors.com

- Sunset

- Sacramento Bee

- San Francisco Chronicle

- Bottlenotes.com

- PubClub.com

- The Willits News

- Smithsonian.com

- VIA

- Coastal Living

- Sacramento Magazine

- 7x7

- Globo News / FJ Productions

- Let's Travel Radio

- The People

We continued our ongoing marketing programs.  Several highlights from the past quarter:

- Researched, wrote and distributed EIGHT press releases to a variety of targeted media. Topics 	included:

- “Beer, Wine & Mushroom Festival” - Distributed to national long leads on 7/12/12

- “What’s New in Mendocino County Summer 2012” - Distributed to local/regional/national long & short leads

- “Scott Schneider Wins ‘Forty for the Future Award’” – Distributed to targeted media in mid-July

- “Mendocino County's Second Annual Festive Fortnight Celebration:  Dec 2012” - Distributed to national long leads on 8/7/12

- “Roots of Motive Power Festival & Kinetic Carnivale Steam Up Mendocino County Sept 8 & 9” - Distributed to local & regional short leads on 8/14/12

- “Fourteen (!) Unique Festivals This Fall in Mendocino, Northern California” – Distributed to local, regional and national short leads + national online editors on 8/23/12

- “Visit Mendocino County Presents The 2012 Annual Tourism Summit” - Distributed to local and regional short leads on 9/5/12

- “International SuperFAM Group Visits Mendocino County Sept 23 & 24” - Distributed to local & regional short leads on 9/27/12

- Secured six person judging panel for 2012 Beer, Wine & Mushroom Festival. Judges include:

- Marne Setton – Saveur

- Christian DeBenedetti – Weekly Pint

- Tina Vierra – Practical Winery & Vineyard Journal

- John Garrone –  Far West Fungi

- Toby Garrone –  Far West Fungi

- Christopher Staten –  DRAFT Magazine

- Initiated revamp of Press Release Distribution Schedule. New press release schedule includes multiple “personality” releases that will focus on unique characters/businesses throughout the county.

- Coordinated press trips for a number of top-tier media, including editors from Bottlenotes.com, Visit California, Caviar Affair, Fodors.com and Der Standard (Austrian newspaper).

- Submitted four events to the Wine Institute for California Wine Month; submitted info for multiple Visit California requests:  California Olive Oil, Halloween Events, What’s New in California Fall 2012, and Pet-friendly.  Also submitted info for the Food Network’s “Cheese” request, Southwest Airlines “Adventure Travel” request, and DK Publishing’s “Rough Guides.”

- Attended and presented at 2012 Tourism Summit at Rivino Winery in Ukiah. Met with VMC team members in Ukiah to review PR goals and for the next year. Attended Ukiah City Hall meeting to support BID increase. Worked the Chocolate Fest in San Francisco in Ghirardelli Square.  Attended Winesong in Fort Bragg.

| PR Quarterly Comparison |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 7-9/2010 | 7-9/2011 |  |  | 7-9/2012 | Total |
| Stories Placed | 18 | 23 |  |  | 20 | 73 |
| Impressions | 27,171,519 | 36,983,622 |  |  | 48,259,584 | 81,322,077 |
| PR Value | $2,098,432 | $1,539,646 |  |  | $1,837,049 | 5,586,642 |
| Editors Toured (Group Tours) | 6 | 6 |  |  | 11 | 24 |

Sales – Group & Leisure

- Attended, for the first time, the Ghirardelli Square Chocolate Festival in San Francisco.  Reached quality demographic.  Distributed over 1,600 famous green bags, receiving over 1,500 email addresses

- Participated once again in Bark in the Park in San Jose receiving close to 1,000 new email addresses

- Inclusion of Mendocino County in numerous international itineraries

- Continued working with UK tour Operator who is bringing 8 groups of from 20-44 through Mendocino County this spring and summer. Was able to secure wine tastings and time for Fort Bragg shopping

- Obtained placement in 2 international tour package guides

- Represented Mendocino County at Annual Western Association of Convention & Visitor Bureau’s Conference

Visitor Services/Fulfillment

- Continued distribution of tear off maps to North Coast businesses. Demand has been so heavy it was necessary to reorder

- Distribution of Willits tear off maps continues

- Distribution of South Coast tear off maps continues

- Construction of kiosk for Boonville is complete.  Working on implementation plan

- Preparing for Excellence in Service – Customer Service Workshop in January

- Continue to work on securing location for gateway sign on Hwy 20 from Lake County

Festivals

Beer, Wine & Mushroom Festival - November 2-11, 2012

- Outreach to past and potential event holders countywide to encourage events, assist with event development ideas and listings in event guide including coordinating dates and times of events to minimize conflicts

- Developed new idea for Passport Grand Prize winner

- Solicited advertising in Event Guide

- Solicited Passport participants among breweries and wineries - 34 wineries and 3 breweries will participate

- Submitted events to VisitMendocino.com to coordinate with Guide

- Met with event planners to discuss festival participation and ideas for new events

- Worked with graphic designer on event guide layout

- Solicited print bids and selected printer; 20,000 full-color 40-page brochures

- Arranged for printing of Beer, Wine & Mushroom event signs

- Began distribution of event guides and signs throughout county to event-holders and strategic locations

- Attended Beer, Wine & Mushroom Train judge/media planning meetings

Crab, Wine & Beer Festival - January 18-27, 2013

- Created and sent out initial call for events and Passport invitations

- Met with Coast Clinics Event Coordinator, MWWC re Cook-off and Wine Competition

- Began compiling event guide listings; invited new businesses to participate

Where the Earth IS First Festival - April 19-28, 2013

- Initiated idea for signature event for festival: olive oil competition and sparkling wine tasting

- Attended meeting of interested parties to discuss

- Researched olive oil and sparkling wine producers in the county

Festive Fortnight

- Came up with new concept for dealing with the 14 days of Festive Fortnight to take advantage of existing events

- Updating branding and logo to coordinate with overall branding

- First draft of Call for Events/Specials

Calendar of Events

- Researched county events and 2013 dates for inclusion in VMC wall calendar

Miscellaneous Festivals/Events/Board & Committee Meetings

- Posted events on Via Magazine website

- Posted events and photos on Visit California website

- Posted events on VisitMendocino.com website

- Attended Kinetic Carnivale, Winesong, Fabulous Flashback Car Show, Mendocino County Fair, and other county events on behalf of VMC; took photos

- Staffed Festival Committee meetings to discuss ongoing festival issues and event guide

- Attended MWWC annual Mendocino County Wine Competition

- Reported on festivals at monthly Board meetings

- Attended Willits Kinetic Carnivale planning meetings

- Kept VMC festival information current on VMC website

Partnerships

- Participate in Mendocino Economic Development Forum in Ukiah

- Attended Anderson Valley Chamber of Commerce mixer

- Attended numerous festivals & events throughout County

- Continued to work closely with MAPA to keep our State Parks open

- Participated in the MWWC’s “Wind Down Committee” working to close out the organization in a responsible and efficient manner

- Worked with the replacement group from the Wine Commission which is now called Mendocino Wine Growers Inc

- Joined the EDFC Board of Directors which is an exciting new partnership promoting economic development throughout the county

- Meetings continue with Anderson Valley Winegrowers Association & Destination Hopland to strengthen partnerships

- Attended California Travel Association Quarterly Board Meetings

- Continued chairmanship of Visit CA Rural Marketing Committee working with industry throughout CA to have visitors “get out there” into rural destinations

North Coast Tourism Council

- Administered NCTC organization including multiple Board meetings

- Attended numerous meetings with San Francisco Travel to encourage greater participation

Administration

- Continued to administer the Mendocino County Promotional Alliance, Mendocino County Lodging Association and North Coast Tourism Council.  Organized meeting packets, facilitated board meetings and composed requested reports

- Distributed a monthly report for the Board of Supervisors and  to other boards and businesses throughout the County

- Continued working on the development of a 2013 Mendocino County wall calendar

- Moved the Fort Bragg office to a new centrally located space in downtown.  This new space allows for more concierge type guest services and provides space for retail opportunities

- VMC 2011-2012 Annual Reports were printed and distributed. Copies are available at each VMC office

- VMC won its first national advertising award.  A Silver medal was won for the Crab & Wine Days from Travel Weekly

- Recently attended a Rural Conference in Sacramento held by Visit California to continue to help market rural areas of the state

MCLA

- Continued to work on coordinating the Jack Rabbit Online Booking System for all lodging properties

- Administered MCLA Board and committees including multiple Board Meetings and Committee Meetings

- Continued to organize, promote and administer several open forums for MCLA members on changing the BID to 2% with a 5 year renewal

- Continued to maintain list serves

- MCLA and VMC hosted the 2012 Annual Tourism Summit in Ukiah at Rivino Winery.  Speakers included both candidates for US Congress as well other tourism related guests.  Over 80 local business owners were in attendance

- MCLA now has an online booking system that is compatible for all members.  Jack Rabbit online booking can be seen in action on www.visitmendocino.com